## Project Baseline
UA Research Upgrade - Project Baseline
Weeks Since Project Start
| Calendar Months | 10 |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
| Total FTE Commit | 6.5625
[5 empty] | DoW | 5 | 11.875 | 11.875 | 11.875 | 11.875 | 11.875 | 16.875 | 45 | 45 | 45 | 45 | 45 | 48.75 | 57.5 | 55 | 55 | 55 | 55 | 58.75 | 62.5 | 55 | 55 | 55 | 55 | 58.75 | 62.5 | 55 | 55 | 55 | 55 | 53.75 | 50.625 | 43.125 | 43.125 | 43.125 | 43.125 | 41.875 | 17.5 | 10 | 10 | 10 | 10 | 10 | 5
Project Staffing |  | Total FTE | Peak FTE | %Util
Functional Office |  | 1.7308 | 3 | 68.18% |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Business Analysts |  | 1.7308 | 3 | 68.18% |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software Developers |  | 1.7308 | 3 | 68.18% |  | 0 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Developer Support |  | 0.45673 | 1.375 | 39.26% |  | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.625 | 0.625 | 0.625 | 0.625 | 0.625 | 0.625 | 0.875 | 0.875 | 0.625 | 0.625 | 0.625 | 0.625 | 0.875 | 1.375 | 0.625 | 0.625 | 0.625 | 0.625 | 0.875 | 1.375 | 0.625 | 0.625 | 0.625 | 0.625 | 0.375 | 1.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0.5
Support Operations |  | 0.33654 | 1.125 | 35.35% |  | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.625 | 0.375 | 0.375 | 0.375 | 0.375 | 0.375 | 0.875 | 0.625 | 0.375 | 0.375 | 0.375 | 0.375 | 0.875 | 1.125 | 0.375 | 0.375 | 0.375 | 0.375 | 0.875 | 1.125 | 0.375 | 0.375 | 0.375 | 0.375 | 0.375 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0.5
Business Intelligence |  | 0.57692 | 1 | 68.18% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Delivery Cycle
|  |  |  | PropDev/Inst Prop |  | ACT | SND | FTR | SCN | SCN | GAP | BKL | PDV | PDV | PDV | PDV | PDV | RLO | ETL | MDL | DSH | RPT | RPT | RPT | DLV
|  |  |  | Functional Office |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  |  | Business Analysis |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Software Development |  | 0 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Development Support |  | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | Support Operations |  | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | Business Intelligence |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  |  | Award | [7 empty] | ACT | SND | FTR | SCN | SCN | GAP | BKL | PDV | PDV | PDV | PDV | PDV | RLO | ETL | MDL | DSH | RPT | RPT | RPT | DLV
|  |  |  | Functional Office | [7 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  |  | Business Analysis | [7 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Software Development | [7 empty] | 0 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Development Support | [7 empty] | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | Support Operations | [7 empty] | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | Business Intelligence | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  |  | IRB | [13 empty] | ACT | SND | FTR | SCN | SCN | GAP | BKL | PDV | PDV | PDV | PDV | PDV | RLO | ETL | MDL | DSH | RPT | RPT | RPT | DLV
|  |  |  | Functional Office | [13 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  |  | Business Analysis | [13 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Software Development | [13 empty] | 0 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Development Support | [13 empty] | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | Support Operations | [13 empty] | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | Business Intelligence | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  |  | Negotiation | [19 empty] | ACT | SND | FTR | SCN | SCN | GAP | BKL | PDV | PDV | PDV | PDV | PDV | RLO | ETL | MDL | DSH | RPT | RPT | RPT | DLV
|  |  |  | Functional Office | [19 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  |  | Business Analysis | [19 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Software Development | [19 empty] | 0 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Development Support | [19 empty] | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | Support Operations | [19 empty] | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | Business Intelligence | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  |  | COI | [25 empty] | ACT | SND | FTR | SCN | SCN | GAP | BKL | PDV | PDV | PDV | PDV | PDV | RLO | ETL | MDL | DSH | RPT | RPT | RPT | DLV
Functional Office | [29 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Business Analysis | [29 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software Development | [29 empty] | 0 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 2.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Support | [29 empty] | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
Support Operations | [29 empty] | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0.5
Business Intelligence | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0

## Per Module Labor
UA Research Upgrade - Per Module Labor Estimate By Phase
|  | Activation | Requirements Gathering (REQS) |  |  |  |  | Functional Remediation (FRMD) |  |  | Knowledge Management (KMGT) |  |  |  | Delivery
|  |  | Sandboxing | Feature Identification | Scenario Scripting | Gap Analysis | Backlog Creation | Release In | Pipelined Development | Release Out | ETL Design | Data Modeling | Dashboard Design | Report Creation
|  | ACT | SND | FTR | SCN | GAP | BKL | RLI | PDV | RLO | ETL | MDL | DSH | RPT | DLV
Days | DAYS | 5 | 5 | 5 | 10 | 5 | 5 | 1 | 24 | 5 | 5 | 5 | 5 | 15 | 5
Labor
Functional Office | FO | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Business Analysis | BA | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Software Development | SD | 0 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 2.875 | 2.875 | 2.875 | 0 | 0 | 0 | 0 | 0
Development Support | DS | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.25 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0.5
Support Operations | SO | 0.5 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0.5
Business Intelligence | BI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0

## Labor Commits
UA Research Upgrade - Estimated Commits By Week
|  | Project Week | [43 empty] | Total %Committed
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
Functional Office
FO-PropDev/InstProp | [Jessica] | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.91%
FO-Award | Susan Mundt | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.91%
FO-IRB | Andi Encinas | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.91%
FO-??? | [tbd] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.91%
FO-??? | [tbd] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 40.91%
Business Analysis
BA-Principal | Kari Robertson | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 68.18%
BA-Senior-1 | Amy Dougherty | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 68.18%
BA-Senior-2 | Jessica Peck | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 68.18%
Software Developers
SD-Principal | Josh Shaloo | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 87.5% | 87.5% | 87.5% | 87.5% | 87.5% | 87.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 68.18%
SD-Senior-1 | Scott Skinner | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 68.18%
SD-Senior-2 | Phil Walters | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 68.18%
Development Support/Operations
DSO-Principal | Heather Lo | 50% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 62.5% | 47.5% | 50% | 50% | 50% | 50% | 87.5% | 47.5% | 50% | 50% | 50% | 50% | 87.5% | 97.5% | 50% | 50% | 50% | 50% | 87.5% | 97.5% | 50% | 50% | 50% | 50% | 37.5% | 85% | 37.5% | 37.5% | 37.5% | 37.5% | 25% | 50% | 0% | 0% | 0% | 0% | 0% | 50% | 43.75%
DSO-Senior | Natalia Costea Ibanez | 16.75% | 4.25% | 4.25% | 4.25% | 4.25% | 4.25% | 20.75% | 15.75% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 32.5% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 50% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 50% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 45% | 12.5% | 12.5% | 12.5% | 12.5% | 8.25% | 32.5% | 0% | 0% | 0% | 0% | 0% | 16.75% | 16.99%
DSO-Senior | Jennifer Hard | 16.75% | 4.25% | 4.25% | 4.25% | 4.25% | 4.25% | 20.75% | 15.75% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 32.5% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 50% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 50% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 45% | 12.5% | 12.5% | 12.5% | 12.5% | 8.25% | 32.5% | 0% | 0% | 0% | 0% | 0% | 16.75% | 16.99%
DSO-Senior | Robert Hunter | 16.75% | 4.25% | 4.25% | 4.25% | 4.25% | 4.25% | 20.75% | 15.75% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 32.5% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 50% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 50% | 16.75% | 16.75% | 16.75% | 16.75% | 30% | 45% | 12.5% | 12.5% | 12.5% | 12.5% | 8.25% | 32.5% | 0% | 0% | 0% | 0% | 0% | 16.75% | 16.99%
Business Intelligence
BI-1 | [tbd] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 68.18%

## Modules By Release
UA Research Upgrade - Modules By Release
Release Date | KC | Rice | Modules | Other Notes
2008-07-01 | 1.0 | 1.0 | Proposal & Budget Development
Institutional Proposal
Grants.gov System-To-System Submission
2008-11-01 | 1.1 | - |  | Interface enhancements.
2009-04-01 | 1.1.1 | - |  | Bug fix release.
2010-04-01 | 2.0 | - | Award
2010-11-01 | 3.0 | - | Institutional Review Board
2011-07-01 | 3.1 | - |  | Enhancements to existing modules.
2011-09-01 | 3.1.1 | - |  | KFS/KC integration work.
2011-12-01 | 3.2 | - |  | Internal release.
2012-03-01 | 4.0 | 2.0 | Conflict Of Interest | Internal release.
|  | - | Subawards
|  | - | Negotiations
|  | - | Report Tracking
2012-06-01 | 5.0 | 2.1 | Institutional Animal Care & Use Committee | KRMS integration.
2012-08-01 | 5.0.1 | - |  | Bug fix release.
2013-04-01 | 5.1 | 2.1.5 |  | Enhancements to existing modules.
2013-07-01 | 5.1.1 | 2.1.7 |  | Bug fix release.
2014-01-01 | 5.2 | - |  | Improved support for Java 7.